## Slide 1: AI 2025: Transforming Forecasting for a Competitive Future
Presented by: Anand Gupta

## Slide 2: Introduction
AI 2025 Project: Strategy, Execution, and Interim Lessons Learned The AI 2025 initiative is a strategic project aimed at revolutionizing the Company’s forecasting and operational capabilities through the integration of AI-driven tools. As the Company prepares for a significant merger with its largest competitor, AI 2025 is crucial for streamlining demand forecasting processes, enhancing decision-making, and reducing operational inefficiencies across both business units.
This project requires effective collaboration between IT, business units, and external vendors to deliver a fully operational AI tool on time and within budget, all while navigating the complexities of stakeholder alignment, change management, and resource planning.
In this presentation, we will cover:
The Project Charter and its strategic goals, roles, and deliverables.
The Project Schedule, including key milestones and their alignment with organizational priorities.
The Budget, ensuring cost-effective execution while maintaining flexibility to address unforeseen challenges.
Interim Lessons Learned, reflecting on the project’s progress so far, identifying gaps, and proposing solutions for continued success.
This comprehensive approach ensures that AI 2025 aligns with the Company’s broader strategic objectives, delivers measurable outcomes, and prepares for a seamless post-merger integration.

## Slide 3: Topics Covered
This presentation provides a comprehensive overview of the AI 2025 Project, covering key aspects of its planning, execution, and interim progress. The following topics are addressed:
Project Charter
Project Purpose & Justification
Roles and Responsibilities
Success Metrics (KPIs)
Key Deliverables
Fee Structure & Incentives
Risks and Assumptions
Project Schedule
Key Milestones and Dates
Alignment with Strategic Goals and Wall Street Expectations
Schedule Feasibility and Risk Mitigation
Budget Overview
Resource Allocation and Costs
Incentive Structure and KPIs
Budget Feasibility and Recommendations
Interim Lessons Learned
Information Gaps and Mitigation Strategies
Stakeholder Engagement and Integration Challenges
Change Management and Workforce Transition
Governance and Role Clarity
Recommendations for Improvement
Conclusion & Next Steps
Project Progress and Strategic Alignment
Moving Forward: Key Areas for Focus

## Slide 4: AI 2025: New Project Charter
Driving Strategic Transformation and Operational Excellence
Project Sponsor: CEO Project Manager: Anand Gupta Approval Date: December 3, 2024

## Slide 5: Project Overview and Purpose
Project Overview
AI 2025 is a transformative initiative to integrate AI-driven forecasting tools, enhance decision-making, and support strategic goals ahead of the Q3 merger.
Purpose and Justification
Enhance forecasting accuracy (>10% improvement).
Streamline operations, achieving $10M in payroll savings annually.
Strengthen market perception by demonstrating technological leadership.
Ensure seamless post-merger integration with unified AI capabilities.

## Slide 6: Roles and Responsibilities
IT Group’s Role
Oversee technical integration and collaboration with TPZ.
Lead training and onboarding processes for AI adoption.
Ensure system compatibility with existing operations.
Project Manager’s Role (Me)
Act as the central leader and point of accountability.
Bridge gaps between stakeholders, business units, and technical teams.
Deliver the project on time, within budget, and aligned with strategic goals.
Provide oversight during planning and tactical guidance during execution.

## Slide 7: Success Metrics (KPIs)
Technical KPIs
Functional AI readiness by April 1 (media announcement).
Tool operational with >95% uptime by Q3 merger deadline.
Financial KPIs
Achieve >$10M in payroll savings.
Minimize severance costs to <$4M.
Operational KPIs
Complete 90% of training programs before full implementation.
Achieve <3% deviation in forecast accuracy during rollout.
Stakeholder KPIs
90% alignment score from business unit leaders by Q2.

## Slide 8: Key Deliverables
Fully functional AI forecasting tool operational by December 1, 2025
Executive-ready dashboard for Wall Street demonstration by April 1, 2025
Comprehensive training programs for business units.
Detailed documentation of forecasting improvements and cost reductions.

## Slide 9: Information Gaps and Mitigation Strategies
Identified Gaps
Stakeholder buy-in from business unit leaders.
Integration details with competitor systems.
Change management strategies for workforce transitions.
Clarity on severance policies.
Mitigation Strategies
Conduct workshops with business units to align objectives.
Perform a detailed assessment of system compatibility.
Develop robust communication and training plans.
Collaborate with HR to manage financial and morale implications.

## Slide 10: Fee Structure and Incentives
Base Fee: $450,000 for project management and oversight.
Incentive Fee: $50,000 tied to achieving:
  AI readiness for media announcement.
  Stakeholder alignment score >90%.
  90% completion of training programs.
Transparency
  Regular reporting on resource utilization and budget adherence.
  Regular updates on Project Schedule and Timeline adherence.

## Slide 11: Risks, Assumptions, and Governance
Risks
Stakeholder resistance and employee attrition.
System integration challenges.
Assumptions
Timely resource availability.
Effective collaboration with TPZ.
Commitment from stakeholders.
Governance Framework
Establish a Steering Committee with senior executives, IT leads, and key stakeholders.
Define decision points for approvals at critical milestones (e.g., prototype completion, training initiation).

## Slide 12: Project Schedule Overview
Objective: To provide a high-level schedule that encompasses technical, operational, and strategic goals, including media events, layoffs, and integration milestones.

## Slide 13: Project Timeline and Milestones

## Slide 14: Broader View
The schedule includes critical non-technical activities:
Wall Street Perception: Delivering a functional dashboard prototype for the April 1 media announcement.
Workforce Transition: Managing layoffs while ensuring operational continuity.
Post-Merger Planning: Ensuring AI is ready to scale for integration with the acquired company.

## Slide 15: Schedule Alignment with Agile
Iterative Development:
  Conduct sprints every four weeks for iterative review and stakeholder feedback.
  Ensure alignment with Agile principles for flexibility and adaptability.
Key Sprint Objectives:
  January-February: Stakeholder engagement and requirement gathering.
  February-March: Prototype development and validation.
  April-August: Integration testing and training program design.
  June-August: Full deployment and change management activities.

## Slide 16: Schedule Feasibility
Does the schedule work?
Early stakeholder alignment (by mid-January) is critical to avoid cascading delays.
Training programs require meticulous planning to fit within the broader timeline.
Risks, such as resistance or delays in integration testing, must be actively mitigated.
Risk Mitigation:
Add buffer time post-integration testing (June) to address unforeseen technical issues.
Employ continuous feedback loops to identify and resolve potential delays.
The timeline aligns with the 270-day completion deadline, but:

## Slide 17: Project Budget Overview
Objective: Align the budget with project goals, fee structure, and resource allocation.

## Slide 18: Resource Allocation and Costs
Resource | Daily Rate | Duration (Days) | Cost
Project Manager (Me) | 1000 | 120 (FT) + 75 (25%) | 157500
Senior Project Manager | 720 | 75 | 54000
Junior Project Manager | 600 | 75 (50%) | 22500
Project Coordinator | 175 | 270 | 47250
Incentive Bonus | - | - | 50000
Contingency Fund | - | - | 18750
Total Budget | - | - | 450000

## Slide 19: Incentive Structure
Base Fee: $450,000 Incentive Bonus: $50,000 (allocated as follows):
AI Readiness for Media Announcement: $15,000
Stakeholder Alignment (>90%): $20,000
90% Training Completion: $15,000

## Slide 20: Budget Feasibility and Recommendations
Is $500,000 Sufficient?
Current budget allocation is feasible within the provided cap.
Contingency fund covers unexpected resource needs or delays.
Should I Ask for More?
Recommend an increase to $550,000 for additional flexibility in case of unforeseen challenges.
Allocation of additional funds to expand training resources if resistance from Forecast Teams grows.
Budget requirement for Pre-Merger and Post-Merger Training
In case of Layoffs, budget requirement for Severance Pay

## Slide 21: Closeout (Interim) Lessons Learned Report

## Slide 22: Lessons Learned
Information Gaps
Stakeholder Alignment: Initial buy-in from business unit leaders was unclear. Without proper engagement, the project risks misaligned priorities.
Solution: Conduct regular workshops and feedback sessions to keep stakeholders aligned with evolving goals.
Integration Details: Insufficient clarity on the technical compatibility between AI 2025 and legacy systems from both business units and the competitor.
Solution: A detailed assessment of existing systems and their alignment with AI 2025 should have been completed early on, along with a phased integration plan.
Change Management: Limited focus on training and managing the transition for Forecast Teams.
Solution: Develop a more comprehensive change management strategy to address concerns about job loss and ensure smooth training adoption.
Severance Costs: Uncertainty surrounding the financial impact of layoffs due to AI implementation.
Solution: Define severance policies early to avoid unexpected financial burdens and smooth employee transitions.

## Slide 23: Personalities and Conflicts
Murat's Leadership Style
Murat’s direct and decisive approach has been effective in driving decision-making but may not always foster the level of collaboration needed with other stakeholders.
Solution: Establish a balance between Murat’s decisiveness and a more consultative approach with business units and technical teams. Create space for feedback loops while maintaining executive alignment.
Helen's Limited Engagement
Helen’s departure and the lack of clarity on her responsibilities left gaps in leadership. Her limited focus on change management and stakeholder engagement caused some friction.
Solution: Ensure that future project transitions include clear handovers and establish robust leadership structures from the outset.

## Slide 24: Roles, Organizational Structure, and Governance
Clear Role Definition
Roles were not always clearly defined between IT, business units, and the project management team. This led to confusion about responsibilities.
Solution: Establish clearer roles and ownership, especially for cross-functional teams like business units and IT. Define clear escalation paths.
Governance Structure
There was no clear, structured governance for decision-making and approval processes, which could slow down progress when approvals were needed.
Solution: Implement a formal governance structure with defined decision-making roles and key approval points.

## Slide 25: Engagement Issues
Forecast Team Resistance
The Forecast Teams’ resistance to AI adoption could delay project goals.
Solution: Early involvement and transparent communication about the benefits of the new tool could have reduced resistance. Including them in early-stage design and feedback loops would have eased the transition.
Wall Street Expectations
The pressure to deliver a fully operational AI tool before the merger’s media announcement could impact quality and employee morale.
Solution: Align Wall Street expectations with realistic timelines and ensure that quality is not sacrificed for speed. A phased, public demonstration of AI capabilities could be a good approach.

## Slide 26: Recommendations for Improvement
Stakeholder Engagement: Focus on continuous, open communication, and keep leadership engaged with regular project status updates.
Integration Planning: Early technical assessments and the creation of a detailed integration roadmap will help mitigate risks.
Change Management: Strengthen change management efforts by addressing team concerns early and ensuring alignment with new processes.
Role Clarity: Clarify roles at the start of the project and maintain a transparent governance structure.
Contingency Planning: Plan for contingencies, especially around layoffs and workforce transitions, ensuring financial and employee well-being.

## Slide 27: Conclusion
The AI 2025 project is on track but requires more structured planning in areas like stakeholder engagement, integration, and change management. Addressing these early challenges will ensure the project remains aligned with its strategic goals and will set the stage for a smoother, successful launch.